## Week1
Project Title: Milestone 4 Release #: 1.2 Sprint #: 4
| # | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | Integration of a logging framework withlog statements for entry to and exit from all major controller, business service, anddata service methods. | Integration of logging framework | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | Integration of documentation framework, such as JavaDoc, PhpDoc, nDoc, or JSDoc, | Bundle Documentation Set | Tim/ Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 2 | As a dev I would like to add features that increase the functionality of my application. | Added features and slight tweaks to design | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | Demonstration of application availability monitoring using an availability provider,such as Uptime Robot | Application availablity monitoring | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 4 | Demonstration of an (semi)automated build pipeline for the application code | Build pipeline | Daniel | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| 5 | As a dev I would like my application hosted in a cloud service | Host to Cloud | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 6 | As a dev I would like a high level video overview of the code, webdesign, and features for presenting current progress. | Loom Video presentation (8 -10 Minutes) | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 7 | As a group we should know who will do the final submit ahead of time to ensure a timely submission. Submission instructions are in the #resources page on Discord chat room. | Final Submission to Loud Cloud | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 8 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 1

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0