## Week1
Project Title: Milestone 3 Release #: 1.1 Sprint #: 3
| # | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I need a paage that allows users to create an account | register page | Tim/Daniel | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
| 2 | As a dev I would likt to provide users with the ability to create or edit posts | create new/ edit post page | Tim/Daniel | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0
| 3 | As a dev I need a page that displays all active posts created by users in one area | post feed page | Tim/Daniel | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
| 4 | As a dev I need a page that allows users to edit their profile details and/ or select if they would like to create or edit posts | my profile page | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 5 | As a dev I would like to provide users with a list of all active posts created by them so they can edit the content | post management page | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 6 | As a dev I would like to have a page that displays one post in a readable manner after a user clicks on a post from the post feed page | view post page | Tim/Daniel | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 7 | As a dev I would like my application hosted in a cloud service | Host to Cloud | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 10 | As a dev I would like a high level video overview of the code, webdesign, and features for presenting current progress. | Loom Video presentation (8 -10 Minutes) | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 11 | As a group we should know who will do the final submit ahead of time to ensure a timely submission. Submission instructions are in the #resources page on Discord chat room. | Final Submission to Loud Cloud |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 12 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 13 | 13 | 13 | 10 | 8 | 3

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0