## Week1
Project Title: Milestone 5 Release #: 1.3 Sprint #: 5
| # | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to have all documentation in a zip file for submission | Zip file of JsDocs documentation | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 2 | As a dev I would like to add features that increase the functionality of my application. | Feature and Design tweaks | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 3 | As a dev I would like my application to be hosted in the cloud. | Cloud Hosting | Daniel | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
| 4 | As a dev I would like a high level video overview of the code, webdesign, and features for presenting the final project. | Final presentation (8 -10 Minutes) | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | As a dev I would like to have a screencast of the current progress of the app for Milestone 5 | Milestone 5 Presentation | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 5 | As a dev I would like a powerpoint presentation for a final project presentation. | PowerPoint Presentation to be used in final presentation. | Tim | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
| 5 | As a group we should know who will do the final submit ahead of time to ensure a timely submission. Submission instructions are in the #resources page on Discord chat room. | Final Submission to Loud Cloud | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 6 | As a dev I would like to have Sprints, burndown chart, and repo setup for project management. | Design and planning documentation | Tim | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 9.4286 | 7.8571 | 6.2857 | 4.7143 | 3.1429 | 1.5714 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 11 | 11 | 10 | 7 | 3 | 0 | 0

## Week2
Project Title: Milestone 2 Release #: 0.1 Sprint #: Spring MVC
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 |  | Main Application Module: menu |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Main Application Module: style |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: active registration |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Registration Module: Database |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database authentication |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: Principle object model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 1 |  | Login Module: database model |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0